## Main Page Summary
MULTI YEAR WORK PLAN
SRIC PROJECT
SUMMARY
[5 empty] | TOTAL ALLOCATION | 4960000
SUMMARY - PLANNED ON PERCENTAGE - Draft Prepared - 12 July 2012
| Summary | ` | 2012 | 2013 | 2014 | 2015 | 2016 | Percentage | PLANNED TOTAL | VS. REVISED SEPT 2010 | Notes
FINAL
| Outcome 1 |  | 6000 | 280000 | 94000 | 10000 | 3000 | 7.863% | 390000
0.8896 | Outcome 2 |  | 12700 | 318300 | 274000 | 75000 | 30000 | 13.71% | 680000
| Outcome 3 |  | 0 | 667000 | 953000 | 820000 | 250000 | 49.19% | 2440000
| Outcome 4 |  | 0 | 15000 | 44000 | 9000 | 16000 | 1.371% | 68000
|  |  | 18700 | 1280300 | 1365000 | 914000 |  | 72.14% | 3578000 | 0
[8 empty] | 4960000 | 1382000
4960000
| REVISED SUMMARY |  | DATE:
| Summary |  | 2012 | 2013 | 2014 | 2015 | 2016 | Percentage | REVISED SEPT 2010 | VS. REVISED DATE XX/XX
[8 empty] | change |  | FINAL
| Outcome 1 | [7 empty] | 0
| Outcome 2 | [7 empty] | 0
| Outcome 3 | [7 empty] | 0
| Outcome 4 | [7 empty] | 0
[8 empty] | 0% | 0 | 0
[6 empty] | 0 |  | 0 | 0
|  |  |  | Unspent Bal. as at ________ | 81143.77
6380.2561
11124.5491
39917.4998
1112.4549
|  |  |  | 0% | 58534.7599

## SRIC MYWP Main
MULTI YEAR WORK PLAN FOR: |  |  |  |  | SRIC - COOK ISLANDS | [13 empty] | First revised | [9 empty] | First revised
PLANNED ACTIVITIES |  |  |  | TIMEFRAME
| 2012 |  |  |  | 2013 |  |  |  |  | 2014 |  |  |  |  | 2015 | [8 empty] | 2016 |  |  |  |  | 2017 |  | Activity Total
| 1 | 3 | 4 | Expenditure | 1 | 2 | 3 | 4 | Budget | 1 | 2 | 3 | 4 | Budget | 1 | 2 | 3 | 4 | Budget | 1 | 2 | 3 | 4 | Budget | 1 | 2 | 3 | 4 | Budget | Budget | Output Total
Outcome 1 : Improved capacity at national level
Output 1.1 Staff trained and working
Activity 1.1.1Trainng of policy makers etc |  | X | X | 2000 | X | X | X | X | 30000 | X | X | X | X | 20000 | [16 empty] | 52000
SUB TOTAL |  |  |  | 2000 |  |  |  |  | 30000 |  |  |  |  | 20000 |  |  |  |  | 0 | [10 empty] | 52000 | 52000
Output 1.2 National and sector policies etc are enhanced
Activity 1.2.1 Strengthen national policies etc |  | X | X | 2000 | X | X | X | X | 8000 | X | X | X | X | 7500 | [16 empty] | 17500
Activity 1.2.2 Strengthen institutional coordination |  |  |  |  | X | X | X | X | 5000 | X | X | X | X | 4500 | [16 empty] | 9500
Activity 1.2.3 Strengthen national curriculum for, and teaching of, DRR and CCA |  |  |  |  | X | X | X | X | 7000 | X | X | X | X | 7000
SUB TOTAL |  |  |  | 2000 |  |  |  |  | 20000 |  |  |  |  | 19000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 41000 | 82000
Output 1.3 Operational climate early warning and information system
Activity 1.3.1 Build capacities of national climate institutions |  | X | X | 2000 | X | X | X | X | 25000 | X | X | X | X | 10000 | [16 empty] | 37000
Activity 1.3.2 Strengthen weather observing networks |  |  |  |  | X | X | X | X | 165000 | X | X | X | X | 28000 | [16 empty] | 193000
Activity 1.3.3 Training for CINMS officials and others |  |  |  |  | X | X | X | X | 5000 | X | X | X | X | 10000
Activity 1.3.4 Establish and implement a climate early warning system |  |  |  |  | X | X | X | X | 20000 | X | X | X | X | 7000 | X | X | X | X | 10000 | X | X | X | X | 7000 | X | X |  |  | 3000
Activity 1.3.5 Establish a framework for a monitoring and surveillance system |  |  |  |  | X | X | X |  | 15000
SUB TOTAL |  |  |  | 2000 |  |  |  |  | 230000 |  |  |  |  | 55000 |  |  |  |  | 10000 |  |  |  |  | 7000 |  |  |  |  | 3000 | 307000 | 604000
OUTCOME 1 - SUBTOTAL |  |  |  | 6000 |  |  |  |  | 280000 |  |  |  |  | 94000 |  |  |  |  | 10000 |  |  |  |  | 7000 |  |  |  |  | 3000 | 400000
Outcome 2 : Improved capacity at Pa Enua level
Output 2.1 Integrated CCA/DRR action plan for each of 11 Pa Enua
Activity 2.1.1 Prepare an integrated CCA/DRR action plan for each of 11 Pa Enua |  |  |  |  | X | X | X | X | 150000 | X | X | X | X | 100000
SUB TOTAL |  |  |  | 0 |  |  |  |  | 150000 |  |  |  |  | 100000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 250000
Output 2.2 Enhanced capcity of Island Councils etc
Activity 2.2.1 - Appoint, train and fund SRIC Focal Points |  |  |  |  | X | X | X | X | 45000 | X | X | X | X | 45000 | X | X | X | X | 15000 | X | X | X | X | 15000 | X | X |  |  | 8000 |  | 105000
Activity 2.2.2 –Train Island Councils, administrations and technical officers |  | X | X | 10200 | X | X | X | X | 75000 | X | X | X | X | 74000 | X | X | X | X | 10000 | X | X | X | X | 10000 | X | X |  |  | 6000 |  | 169200
Activity 2.2.3 Train technical officers etc |  |  |  |  | X | X | X | X | 15000 | X | X | X | X | 15000 | X | X | X | X | 10000 | X | X | X | X | 10000 | X | X |  |  | 6000 |  | 40000
Activity 2.2.4 Train farmers , fishers, households and business owners |  |  |  |  | X | X | X | X | 20000 | X | X | X | X | 20000 | X | X | X | X | 20000 | X | X | X | X | 20000 | X | X |  |  | 10000 |  | 60000
Activity 2.2.5 Establish and implement arrangements to build capacity in the Pa Enua |  | X | X | 2500 | X | X | X | X | 5000 | [21 empty] | 7500
Activity 2.2.6 Administer and manage the SRIC SGP |  |  |  |  | X | X | X | X | 8300 | X | X | X | X | 20000 | X | X | X | X | 20000 | X | X | X | X | 20000 | [6 empty] | 48300
SUB TOTAL |  |  |  | 12700 |  |  |  |  | 168300 |  |  |  |  | 174000 |  |  |  |  | 75000 |  |  |  |  | 75000 |  |  |  |  | 30000 | 535000 | 965000
OUTCOME 2 - SUBTOTAL |  |  |  | 12700 |  |  |  |  | 318300 |  |  |  |  | 274000 |  |  |  |  | 75000 |  |  |  |  | 75000 |  |  |  |  | 30000 | 785000
Outcome 3 Enhanced resilience of 11 inhabited Pa Enua
Output 3.1 Small grants to 11 Pa Enua and their communities
Activity 3.1.1 - Fund the SRIC SGP |  |  |  |  | X | X | X | X | 75000 | X | X | X | X | 75000 | X | X | X | X | 75000 | X | X | X | X | 75000 | X | X |  |  | 10000 |  | 310000
Activity 3.1.2 Implement approved DRR and CCA initiatives using the small grants modality |  |  |  |  | X | X | X | X | 25000 | X | X | X | X | 25000 | X | X | X | X | 25000 | X | X | X | X | 25000 | X | X |  |  | 10000 |  | 110000
SUB TOTAL |  |  |  | 0 |  |  |  |  | 100000 |  |  |  |  | 100000 |  |  |  |  | 100000 |  |  |  |  | 100000 |  |  |  |  | 20000 | 420000 | 420000
Output 3.2 Climate resilient agricultural and fisheries practices
Activity 3.2.1 -Implement DRR/CCA actions that address the full cycle of food production |  |  |  |  | X | X | X | X | 150000 | X | X | X | X | 100000 | X | X | X | X | 75000 | X | X | X | X | 50000 | X | X |  |  | 15000 |  | 390000
Output 3.3 Water management capacities enhanced
Activity 3.3.1 Implement DRR/CCA through integrated water management approaches |  |  |  |  | X | X | X | X | 50000 | X | X | X | X | 75000 | X | X | X | X | 80000 | X | X | X | X | 80000 | X | X |  |  | 75000 |  | 360000
Output 3.4 Coastal protection enhanced
Activity 3.4.1 Implement coastal protection activities to manage climate change risks |  |  |  |  | X | X | X | X | 100000 | X | X | X | X | 100000 | X | X | X | X | 100000 | X | X | X | X | 100000 | X | X |  |  | 60000 |  | 460000
Output 3.5 Resilience of tourism enterprises emhanced
Activity 3.5.1 Implement activities that will enhance the resilience of tourism enterprises |  |  |  |  | X | X | X | X | 10000 | X | X | X | X | 60000 | X | X | X | X | 40000 | X | X | X | X | 30000 | X | X |  |  | 20000 |  | 160000
Output 3.6 Health support and vector-borne control introduced
Activity 3.6.1 Inplement integrated disease prevention, control and response measures |  |  |  |  | X | X | X | X | 40000 | X | X | X | X | 60000 | X | X | X | X | 50000 | X | X | X | X | 30000 | X | X |  |  | 10000 |  | 190000
Output 3.7 Implement infrastructure projects
Activity 3.7.1 Implement priority infrastructure interventions |  |  |  |  | X | X | X | X | 217000 | X | X | X | X | 458000 | X | X | X | X | 375000 | X | X | X | X | 135000 | X | X |  |  | 50000 |  | 1235000
SUB TOTAL |  |  |  | 0 |  |  |  |  | 567000 |  |  |  |  | 853000 |  |  |  |  | 720000 |  |  |  |  | 425000 |  |  |  |  | 230000 |  | 3215000
OUTCOME 3 - SUB TOTAL |  |  |  | 0 |  |  |  |  | 667000 |  |  |  |  | 953000 |  |  |  |  | 820000 |  |  |  |  | 525000 |  |  |  |  | 250000 | 3215000
Outcome 4. Lessons learned and best practices improve effectiveness
Output 4.1 Lessons learned and best practices
Activity 4.1.1 – Generate lessons learned and best practices | [14 empty] | X | X | X | X | 6000 | X | X | X | X | 10000 | X | X |  |  | 10000 |  | 26000
Activity 4.1.2 – Distribute lessons learned and best practices | [19 empty] | X | X | X | X | 6000 | X | X |  |  | 6000 |  | 12000
Activity 4.1.3 – Prepare and evaluate training materials |  |  |  |  | X | X | X | X | 15000 | X | X | X | X | 44000 | X | X |  |  | 3000 | [11 empty] | 62000
SUB TOTAL | [8 empty] | 15000 |  |  |  |  | 44000 |  |  |  |  | 9000 |  |  |  |  | 16000 |  |  |  |  | 16000 |  | 100000
OUTCOME 4 - SUB TOTAL |  |  |  | 0 |  |  |  |  | 15000 |  |  |  |  | 44000 |  |  |  |  | 9000 |  |  |  |  | 16000 |  |  |  |  | 16000 | 100000
Outcome 5. Effective and efficient project management
Output 5.1 Project Management Unit established and operational
Activity 5.1.1 – Project staff recruited |  | X | X | 14238 | X | X | X | X | 56762 | X | X | X | X | 70000 | X | X | X | X | 70000 | X | X | X | X | 70000 | X | X |  |  | 35000 |  | 316000
Activity 5.1.2 – Office furniture, equipment and stationery procured |  | X | X | 11369.2 | X | X | X | X | 11130.8 | X | X | X | X | 4500 | X | X | X | X | 4500 | X | X | X | X | 4500 | X | X |  |  |  |  | 36000
Activity 5.1.3 – PMU operational and supporting project implementation |  |  |  | 8000 | X | X | X | X | 10000 | X | X | X | X | 10000 | X | X | X | X | 9000 | X | X | X | X | 9000 | X | X |  |  | 2000 |  | 48000
SUB TOTAL |  |  |  | 33607.2 |  |  |  |  | 77892.8 |  |  |  |  | 84500 |  |  |  |  | 83500 |  |  |  |  | 83500 |  |  |  |  | 37000 |  | 400000
Output 5.2 Programme Monitoring and Evaluation
Activity 5.2.1 Inception Report |  | X | X | [27 empty] | 0
Activity 5.2.2 – Quarterly Reports |  | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X | X | X |  | X | X |  |  |  |  | 0
Activity 5.2.3 – Six monthly technical monitoring |  |  | X |  |  | X |  | X |  |  | X |  | X |  |  | X |  | X |  |  | X |  | X |  |  | X |  |  |  |  | 0
Activity 5.2.4 – Meetings of National Platform for DRM and CCA |  | X | X |  |  | X |  | X |  |  | X |  | X |  |  | X |  | X |  |  | X |  | X |  |  | X |  |  |  |  | 0
Activity 5.2.5 Annual Audits |  |  | X |  |  |  |  | X | 2000 |  |  |  | X | 2000 |  |  |  | X | 2000 |  |  |  |  | 2000 |  | X |  |  | 2000 |  | 10000
Activity 5.2.6 Mid-term Evaluation | [12 empty] | X | 20000 | [11 empty] | X |  |  |  |  | 20000
Activity 5.2.7 Final Programme Evaluation | [28 empty] | 30000 |  | 30000
Activity 5.2.8 Programme Terminal Report | [30 empty] | 0
0
SUB TOTAL |  |  |  | 0 |  |  |  |  | 2000 |  |  |  |  | 22000 |  |  |  |  | 2000 |  |  |  |  | 2000 |  |  |  |  | 32000 |  | 60000
OUTCOME 5 - SUB-TOTAL |  |  |  | 33607.2 |  |  |  |  | 79892.8 |  |  |  |  | 106500 |  |  |  |  | 85500 |  |  |  |  | 85500 |  |  |  |  | 69000 | 460000
TOTAL MULTI YEAR WORK PLAN BUDGET |  |  |  | 52307.2 |  |  |  |  | 1360192.8 |  |  |  |  | 1471500 |  |  |  |  | 999500 |  |  |  |  | 708500 |  |  |  |  | 368000
TOTAL ANNUAL WORK PLAN |  |  |  | 4960000

## SRIC 2013 AWP
SRIC Annual Work Plan - Year 2013
TIMEFRAME
EXPECTED OUTPUTS | PLANNED ACTIVITIES | Q1 | Q2 | Q3 | Q4 | Budget Description | Amount in US Dollars
Outcome 1 : Improved capacity at national level
Output 1.1 Staff trained and working | Activity 1.1.1Trainng of policy makers etc
| TA for learning needs assessment | [5 empty] | 15000
Indicator: Number of staff with DRR/CCA in their job descriptions and number of staff who have received relevant training | Call for proposals from perferred training providers for national level activities | [5 empty] | 1000
| Evaluate proposals and contract providers | [5 empty] | 2000
Baseline: Zero staff other than those in CCCI and EMCI | First tranche of training | [5 empty] | 12000
Target: 75 staff and 100 staff, respectively, by end of 5th year
|  | (A) Subtotal of Output 1.1 |  |  |  |  | 30000
Output 1.2 National and sector policies etc are enhanced | Activity 1.2.1 Strengthen national policies etc | [5 empty] | 8000
| Activity 1.2.2 Strengthen institutional coordination | [5 empty] | 5000
Indicator: Number of national policies and related enhanced in ways that support CCA and DRR | Activity 1.2.3 Strengthen national curriculum for, and teaching of, DRR and CCA | [5 empty] | 7000
Baseline: Relevant national policy instruments, coordination mechanisms and institutiona do not address climate risks in an adequate manner
Target: By end of fourth yeara at least four relevant national policy instruments, coordination mechanisms and institutiona do not address climate risks in an adequate manner
|  |  | (B) Subtotal of Output 1.2 |  |  |  | 20000
Output 1.3 Operational climate early warning and information system | Activity 1.3.1 Build capacities of national climate institutions | [5 empty] | 25000
Indicator: Fully functional weather observing and reporting systems in the 11 Pa Enua; established and tested early warning system | Activity 1.3.2 Strengthen weather observing networks | [5 empty] | 165000
Baseline: No observing system in the Pa Enua is fully functional; no established and tested early warning system | Activity 1.3.3 Training for CINMS officials and others | [5 empty] | 5000
Target: By end of 5th year all Pa Enua have fully functional weather observing and reporting systems; early warning system fully functional | Activity 1.3.4 Establish and implement a climate early warning system | [5 empty] | 20000
| Activity 1.3.5 Establish a framework for a monitoring and surveillance system | [5 empty] | 15000
|  | (C) Subtotal of Output 1.3 |  |  |  |  | 230000
|  | (A + B + C) Total of Outcome 1: |  |  |  |  | 280000
Outcome 2 : Improved capacity at Pa Enua level
Output 2.1 Integrated CCA/DRR action plan for each of 11 Pa Enua | Activity 2.1.1 Prepare an integrated CCA/DRR action plan for each of 11 Pa Enua | [5 empty] | 150000
Indicator: Number of Pa Enua with with integrated CCA and DRR plans
Baseline: zero
Target: By end of 3rd year all Pa Enua have integrated CCA and DRR plans
|  | (D) Subtotal of Output 2.1 |  |  |  |  | 150000
Output 2.2 Enhanced capcity of Island Councils etc | Activity 2.2.1 - Appoint, train and fund SRIC Focal Points | [5 empty] | 45000
| Activity 2.2.2 –Train Island Councils, administrations and technical officers | [5 empty] | 75000
| Activity 2.2.3 Train technical officers etc | [5 empty] | 15000
| Activity 2.2.4 Train farmers , fishers, households and business owners | [5 empty] | 20000
Indicator: 1) SRIC Focal Points for each inhabited Pa Enua appointed and funded; 2) Island stakeholders and key players trained in climate and disaster risk assessment and management | Activity 2.2.5 Establish and implement arrangements to build capacity in the Pa Enua | [5 empty] | 5000
| Activity 2.2.6 Administer and manage the SRIC SGP | [5 empty] | 8300
Baseline: Island stakeholders and key players have little practical understanding of climate and disaster risk assessment, and how this understanding can contribute to sustainable island development
Target: By the end of the third year at least 500 island stakeholders and players have been trained in climate and disaster risk assessment and management, involving both women and men in an equitable manner
|  | (E) Subtotal of Output 2.2 |  |  |  |  | 168300
|  | D + E Total Outcome 2 |  |  |  |  | 318300
Outcome 3 Enhanced resilience of 11 inhabited Pa Enua
Output 3.1 Small grants to 11 Pa Enua and their communities | Activity 3.1.1 - Fund the SRIC SGP | [5 empty] | 75000
| Activity 3.1.2 Implement approved DRR and CCA initiatives using the small grants modality | [5 empty] | 25000
Indicator: Number of succesfully completed capacity building projects funded by the SRIC Small Grants Programme
Baseline: It is exceedingly difficult for stakeholders in the Pa Enua to access the GEF/UNDP SGP; that programme no longer funds capacity building initiatives
Target: By the end of the 3rd year at least 50 initiatives to build capacity in climate and disaster risk managemenet are funded by the small grants programme, and are completed successfully, involving both men and women in and equitable manner
|  | (F) Subtotal of Output 3.1 |  |  |  |  | 100000
Output 3.2 Climate resilient agricultural and fisheries practices
Indicator: Number of households with enhanced capacity to reduce climate-induce disturbances in food supply through applying climate resilient agriculture and fisheries techniques | Activity 3.2.1 -Implement DRR/CCA actions that address the full cycle of food production | [5 empty] | 150000
Baseline: Currently the estimated 920 households engaged principally in subsistence agriculture or fishing activities in the 5 islands are ill-prepared to adapt to climate change impacts. They lack the capacity to apply adequate land management, crop cultivation and fisheries techniques, and food storage methods, consequently being affected by climate-induced disturbances of food supply, such as droughts or cyclones
Target: By the end of the programme at least 750 households have increased capacity in applying climate resilient agriculture and fisheries practices in at least 5 islands (Aitutaki, Atiu, Manihiki, Mangaia and Mauke)
|  |  | (G) Subtotal of Output 3.2 |  |  |  | 150000
Output 3.3 Water management capacities enhanced
Indicator: Increase in the volume (Litres) of water storage capacity in communities affected by climate-induced water shortages | Activity 3.3.1 Implement DRR/CCA through integrated water management approaches | [5 empty] | 50000
Baseline: The current estimated total water storage capacity in the 11 Pa Enua is about 7 M L. The current open reservoir of 10 M L in Ruaau, and Akaoa (Rarotonga), is completely dysfunctional and needs to be repaired or replaced by another type of storage facility. The infrastructure (e.g. pumps, pipes, guttering) supplying the storage facilities are in poor status reducing efficiency of supply, needing upgrade and maintenance, to satisfy demand and to face climate-induced disturbances in water supply.
Target:By the end of the programme the water storage capacity is increased by at least 14 M L in affected communities as a result of the water infrastructure adaptation projects implemented in at least 7 islands (Aitutaki, Atiu, Mangaia, Mitiaro, Palmerston, Pukapuka and Nassau and Rarotonga )
|  |  | (H) Subtotal of Output 3.3 |  |  |  | 50000
Output 3.4 Coastal protection enhanced
Indicator: Km of coastline with climate resilient shoreline protection measures introduced | Activity 3.4.1 Implement coastal protection activities to manage climate change risks | [5 empty] | 100000
Baseline: Currently coastal protection measures applied by communities are ad-hoc and piecemeal, limited to some vegetation planting along the shore, but lacking the capacity to introduce shoreline protection measures in a planned and systematic way.
Target: Bt the end of the 3rd year at least 50 initiatives to build capacity in climate and disaster risk managemenet are funded by the small grants programme, and are completed successfully, involving both men and women in and equitable manner
Indicator: Number of succesfully completed capacity building projects funded by the SRIC Small Grants Programme |  | (I) Subtotal of Output 3.4 |  |  |  |  | 100000
Output 3.5 Resilience of tourism enterprises emhanced
Indicator: Number of local tourism enterprises applying climate resilient management techniques | Activity 3.5.1 Implement activities that will enhance the resilience of tourism enterprises | [5 empty] | 10000
Baseline: The total number of tourism enterprises in these 3 islands is 67, 54 of these are located in Aitutaki. Currently tourism operators cope with climate-induced impacts (like water shortage, coastal erosion) in an ad-hoc fashion, lack capacity to undertake integrated adaptation measures
Target: By the end of the programme at least 50 local tourism enterprises apply climate resilient adaptation techniques in at least 3 islands (Aitutaki, Atiu and Manihiki)
|  |  | (J) Subtotal of Output 3.5 |  |  |  | 10000
Output 3.6 Health support and vector-borne control introduced
Indicator: Number of households with access to enhanced health services and practices adapting to climate-induced health risks | Activity 3.6.1 Inplement integrated disease prevention, control and response measures | [5 empty] | 40000
Baseline: The total number of households in these 5 islands is 460. Current prevention activities are limited to occasional cleanup programmes (tutaka) to control areas of stagnant water, while there is inadequate capacity of health staff to diagnose and respond to climate-related illnesses.
Target: By the end of the programme at least 400 households have access to enhanced health services and practices in at least 5 islands (Mangaia, Mauke, Mitiaro, Palmerston and Pukapuka)
|  |  | (K) Subtotal of Output 3.6 |  |  |  | 40000
Output 3.7 Implement infrastructure projects
Indicator: Number of households with enhanced capacity to reduce climate-induce disturbances in food supply through applying climate resilient agriculture and fisheries techniques | Activity 3.7.1 Implement priority infrastructure interventions | [5 empty] | 217000
Baseline: Currently the estimated 920 households engaged principally in subsistence agriculture or fishing activities in the 5 islands are ill-prepared to adapt to climate change impacts. They lack the capacity to apply adequate land management, crop cultivation and fisheries techniques, and food storage methods, consequently being affected by climate-induced disturbances of food supply, such as droughts or cyclones
Target: By the end of the programme at least 750 households have increased capacity in applying climate resilient agriculture and fisheries practices in at least 5 islands (Aitutaki, Atiu, Manihiki, Mangaia and Mauke)
|  |  | (L) Subtotal of Output 3.7 |  |  |  | 217000
|  | Total Outcome 3 |  |  |  |  | 667000
Outcome 4. Lessons learned and best practices improve effectiveness
Output 4.1 Lessons learned and best practices | Activity 4.1.1 – Generate lessons learned and best practices
Indicator: Number of knowledge materials generated on lessons learned and best practices, | Activity 4.1.2 – Distribute lessons learned and best practices
Baseline: There is no systematic programme in the Cook Islands to capture lessons learned and best practices in adaptation, disaster risk reduction, and related projects, and disseminate them for wider use | Activity 4.1.3 – Prepare and evaluate training materials | [5 empty] | 15000
Target: At least 5 knowledge materials (experience notes, case studies, photo stories, videos, etc,) are generated per year starting from year 1 of the programme
|  |  | Total Outcome 4 |  |  |  | 15000
Outcome 5. Effective and efficient project management
Output 5.1 Project Management Unit established and operational | Activity 5.1.1 – Project staff recruited | [5 empty] | 56762
| Activity 5.1.2 – Office furniture, equipment and stationery procured | [5 empty] | 11130.8
| Activity 5.1.3 – PMU operational and supporting project implementation | [5 empty] | 10000
|  |  | Subtotal Output 5.1 |  |  |  | 77892.8
Output 5.2 Programme Monitoring and Evaluation | Activity 5.2.1 Inception Report
Activity 5.2.2 – Quarterly Reports
Activity 5.2.3 – Six monthly technical monitoring
Activity 5.2.4 – Meetings of National Platform for DRM and CCA
| Activity 5.2.5 Annual Audits | [5 empty] | 2000
Activity 5.2.6 Mid-term Evaluation
Activity 5.2.7 Final Programme Evaluation
Activity 5.2.8 Programme Terminal Report
|  |  | Subtotal Output 5.2 |  |  |  | 2000
|  |  | Total Outcome 5 |  |  |  | 79892.8
| Total AWP 2013 Budget for SRIC Samoa | [5 empty] | 1360192.8

## Atlas AWP 2013 breakdown
SOF Outcome/ATLAS Activity | Atlas Budget Description | Atlas Budgetary Account Code | Amount Year 2013 (USD)
OUTCOME 1: | International Consultants | 71200 | 15000
| Equipment (CLEWS) | 7220 | 165000
| Local Consultants | 71300 | 44000
| Workshop and Trainings | 72100 | 25000
| Travel | 71600 | 21000
| Supplies | 72300 | 5000
| Audiovisual & Print Production Costs | 74200 | 5000
| TOTAL OUTCOME 1: |  | 280000
OUTCOME 2 | Contractual services | 72100 | 157300
| International Consultant | 71200 | 10000
| Local Consultants | 71300 | 35000
| Workshop and Trainings | 72100 | 75000
| Travel | 71600 | 20000
| Equipment | 7220 | 5000
| Materials and goods | 72300 | 10000
| Audiovisual & Print Production Costs | 74200 | 6000
| TOTAL OUTCOME 2: |  | 318300
OUTCOME 3 | International Consultant | 71200 | 6500
| Local Consultants | 71300 | 180000
| Workshop and Trainings | 72100 | 140500
| Audiovisual & Print Production Costs | 74200 | 20000
| Travel | 71600 | 60000
| Grants | 72600 | 140000
| Materials and goods | 72300 | 110000
| Office supply | 72300 | 10000
| TOTAL OUTCOME 3: |  | 667000
OUTCOME 4 | Local Consultants | 71300
| Travel | 71600
| Equipment & Furniture | 72200
| Office Supplies | 72500
| Professional Services | 71400 | 15000
15000
OUTCOME 5 | Local Consultants | 71300 | 51762
| Travel | 71600 | 10000
| Equipment & Furniture | 72200 | 11130.8
| Office Supplies | 72300 | 5000
| Professional Services | 71400 | 2000
79892.8
| TOTAL ANNUAL YEAR BUDGET 2012 |  | 1360192.8

## Blank
SRIC 3rd Quarter Work Plan - Year 2012
TIMEFRAME
EXPECTED OUTPUTS | PLANNED ACTIVITIES | July | Aug | Sept | Budget Description ATLAS | Amount in SAT Dollars
Outcome 1 :
Output 1.2 | Activity:
Indicator:
Target:
|  | (A) Subtotal of Output 1.2 |  |  |  | 0
(A + B = C) Total of Outcome 1:
Outcome 2 :
Output 2.1 | Activity:
Indicator:
Baseline:
Target:
|  | (D) Subtotal of Output 2.1 |  |  |  | 0
D + E= F) Total Outcome 2
Outcome 3 :
Output 3.1
Indicator:
Baseline:
Target:
|  | (G + H = I) Total Outcome 3 |  |  |  | 0
Outcome 4.
Output 4.1
Indicator:
Baseline:
Target:
| Exchange rate: NZD - USD: | (J) Subtotal of Outcome 4: |  |  |  | 0
0
Indicator
Baseline
Target
0
|  | (K) Total Outcome 4 |  |  |  | 0
Total 3rd Quarter Planned Budget
298554
PREPARED BY
APPROVED BY

## Sheet1 (hidden)
ICCRIFS 3rd Quarter Work Plan - Year 2011
TIMEFRAME
EXPECTED OUTPUTS | PLANNED ACTIVITIES | July | Aug | Sept | Budget Description ATLAS | Amount in US Dollars
Outcome 1 : Climate risk and resilience integrated into lowland agroforestry and upland native forestry policies, strategies and management techniques
Output 1.2 Forestry-tailored climate early warning and information system developed | Activity: |  |  |  | 71200 | 7000
Indicator:
Target:
|  | (A) Subtotal of Output 1.2 |  |  |  | 7000
|  | (A + B = C) Total of Outcome 1: |  |  |  | 7000
Outcome 2 : Climate resilient agro-forestry and forestry techniques are demonstrated in lowland and upland areas
Output 2.1 and 2.2: Climate-resilient agroforestry techniques are demonstrated in upland/lowland native forestry areas in customary lands at the mid-North Coast lowlands | Activity: |  |  |  | 75700 | 5000
Indicator: | Activity: |  |  |  | 75700 | 5000
Baseline:
Target:
|  | (D) Subtotal of Output 2.1 |  |  |  | 10000
|  | D + E= F) Total Outcome 2 |  |  |  | 10000
Outcome 3 : Project knowledge captured, analyzed and disseminated
Indicator:
Baseline:
Target:
|  | (G + H = I) Total Outcome 3 |  |  |  | 0
Outcome 4. Project Management
Output 4.1 Effective Project Management | Activity 4.1.1 – Recruitment of PMU
Indicator: | Coordinator (6 payments) |  |  |  | 71300 | 5000
| Assistant (6 payments) |  |  |  | 71300 | 3000
Recruitment of Technical Officer:
Tech. Officer Agroforestry, Tech. Officer native trees , Media Officer
( 5 payments for each officer)
Baseline: | Activity 4.1.8– Purchase of PMU equipments (2 laptops,) |  |  |  | 72200 | 11000
Target: | activity 4.1.9 - Purchase of office supplies (2 desks, 2 chairs, 2 bookshelves, 2 cabinets) |  |  |  | 72200 | 2200
Purchase of Project vehicle for project implementation
| Exchange rate: WST - USD: 2.32 | (J) Subtotal of Outcome 4: |  |  |  | 21200
21200
Indicator
Baseline
Target
0
|  | (K) Total Outcome 4 |  |  |  | 21200
| Total 2nd Quarter Planned Budget |  |  |  |  | 38200