- Mitig Adapt Strateg Glob Change (2011) 16:845–863 DOI 10.1007/s11027-011-9298-6

- ORIGINAL ARTICLE

- Building responsiveness to climate change through community based adaptation in Bangladesh

- Amireeta K. Rawlani & Benjamin K. Sovacool

- Received: 5 March 2011 /Accepted: 10 May 2011 / Published online: 24 May 2011 © Springer Science+Business Media B.V. 2011

- Abstract This article explores the drivers, benefits, and challenges to climate change adaptation in Bangladesh. It specifically investigates the “Community Based Adaptation to Climate Change through Coastal Afforestation Program,” a 5-year $5 million adaptation scheme being funded and implemented in part by the Government of Bangladesh, United Nations Development Program, and Global Environment Facility. The article explores how the CBACC-CA builds various types of adaptive capacity in Bangladesh and the extent its design and implementation offers lessons for other adaptation programs around the world. The first part of the study begins by describing its research methods consisting of research interviews, site visits, and a literature review. It then summarizes six primary sectors vulnerable to climate change in Bangladesh: water resources and coastal zones, infrastructure and human settlements, agriculture and food security, forestry and biodiversity, fisheries, and human health. The article next describes the genesis and background behind the CBACC-CA, with an emphasis on components that promote capacity development, demonstration projects, risk reduction, and knowledge management. The article concludes that technology by itself is only a partial component of successful adaptation efforts, and that multiple and integrated adaptation measures that cut across sectors and social, institutional, and infrastructural dimensions are needed to truly build resilience and effectiveness.

- Keywords Bangladesh

- .

- Community based adaptation

- .

- Climate change adaptation

- . Coastal afforestation

- 1 Introduction

- Bangladesh contributes little to global greenhouse gas emissions yet is one of the most vulnerable countries to climate change. Because it sits at the intersection of three major

- A. K. Rawlani

- .

- B. K. Sovacool (*) Lee Kuan Yew School of Public Policy, National University of Singapore, 469C Bukit Timah Road, Singapore 259772, Singapore e-mail: bsovacool@nus.edu.sg

- A. K. Rawlani e-mail: amireeta@nus.edu.sg

- river basins and features flat deltaic topography with low elevation (Fig. 1), it is prone to a multitude of climate-related events such as floods, droughts, tropical cyclones and storm surges. Fifteen percent of its 162 million people live within one-meter elevation from high tide (Matthew 2007), yet annual floods inundate between 20 and 70% of the country’s landmass each year (Mirza 2002). Bangladesh has high population density and rates of poverty, being the seventh most populous country in the world with a density greater than one thousand persons per square kilometer, and yearly per capita income ranging between $400 and $1,700 (depending on what one counts and whether they adjust for purchasing power parity). Bangladesh also has extreme climate variability, naturally alternating between seasons of monsoon and winter drought, and it is dependent on crop agriculture, highly sensitive to changes in climate (Ahmed 2006). It is reputed to be the most vulnerable country in the world to tropical cyclones and the sixth most vulnerable country to floods.

- Thus, building responsiveness to climate change through adaptation has been recognized as necessary to the very political and economic survival of the country (Ali 1999; Sajjaduzzaman et al. 2005). This article therefore investigates one prominent, and successful, adaptation project currently being implemented there: the “Community Based Adaptation to Climate Change through Coastal Afforestation” Program, or CBACC-CA. The CBACC-CA is a 5-year $5 million adaptation scheme being funded and implemented by the Government of Bangladesh, United Nations Development Program, and the Global Environment Facility. The article asks: in what ways does the CBACC-CA strengthen adaptive capacity, and what lessons does its design and implementation offer other adaptation programs around the world?

- The first part of the article summarizes its research methods, consisting of research interviews, site visits, and a literature review. The article then identifies six primary sectors vulnerable to climate change in Bangladesh. It next emphasizes components of the

- 846 Mitig Adapt Strateg Glob Change (2011) 16:845–863

- Fig. 1 The river systems of Bangladesh. Source: Mirza 2002: 128

- Mitig Adapt Strateg Glob Change (2011) 16:845–863 847

- CBACC-CA that promote capacity development, demonstration projects, risk reduction, and knowledge management. Achieved and anticipated benefits include improving physical responsiveness by deploying “soft” and “indigenous” infrastructure through the creation of green coastal belts, the enhancement of institutional effectiveness by training policymakers, and the strengthening of community knowledge by providing alternative livelihood options and establishing early warning systems. Challenges include ensuring that adaptation efforts are enough to truly respond to climate vulnerability, lack of coordination, and growing yet still constrained institutional capacity to ensure successful implementation.

- The novelty of such an exploration is fourfold. First, our study focuses intimately on the benefits to climate change adaptation, which may be more appropriate and effective than mitigation for least developed countries such as the Bangladesh as well as other coastal countries and Small Island Developing States. Adapting to climate-related impacts will only become more salient over time for these countries. Second, the article treats adaptive capacity as multidimensional, inclusive of physical measures such as improved infrastruc- ture or stronger technology alongside institutional measures such as good governance and political awareness and social measures such as standards of living and community assets. Third, it investigates the challenges facing adaptation efforts in practice, barriers that will have to be overcome on the ground of infrastructural, institutional, and community effectiveness are to be meaningfully strengthened in Bangladesh and elsewhere. Fourth is our utilization of a mixed methods approach that relies not only on original primary data collected through in-country interviews and visits but also secondary data from peer- reviewed literature and reports.

- 2 Research methods

- In order to better understand the expected impacts from climate change in Bangladesh, the authors conducted research interviews at various institutions throughout the country including the Bangladesh Ministry of Environment and Forests, United Nations Development Program Bangladesh, Bangladesh Forest Department, and the Bangladesh Forest Research Institute. Questions were qualitative, open-ended, and mainly related to Bangladesh’s vulnerability to climate change, strengths and weaknesses of its national climate policy, and specific details of the CBACC-CA project. Reponses were transcribed and then coded, although data from these interviews is quoted throughout the article as anonymous in order to maintain confidentiality at the request of participants and adhere to institutional review board guidelines. To further study the conditions of the vulnerable coastal communities, three site visits were made to the districts of Noakhali, Chittagong and Cox’s Bazaar, where the authors arranged meetings with local scientists, community leaders, farmers, and residents of vulnerable communities, and asked them about the costs and benefits of local efforts related to the CBACC-CA project.

- In structuring the interview questions, the authors elected to employ an inductive approach to minimize interpretative bias caused by researchers trying to force responses into preset cognitive frameworks. This inductive approach was implemented by fixing our initial questions for each interview and then allowing interview subjects to respond in as much detail as they wanted. The four questions were: i) “What are the primary climate change risks facing Bangladesh?;” ii) “How well does national policy address these risks?;” iii) “What are some of the challenges facing adaptation projects such as the CBACC-CA?;” and iv) “What are some of the benefits and lessons learned from the

- 848 Mitig Adapt Strateg Glob Change (2011) 16:845–863

- CBACC-CA?”. The authors supplemented these four questions with “probing response techniques” when clarification or elaboration was sought and “reflecting response techniques” in order to elicit deeper responses when warranted (Sovacool and Valentine 2011). In response to these interviewing strategies, participants introduced new topics into the conversation not anticipated by the authors. Interviews lasted between 30 and 90 min, site visits between 1 and 4 h.

- These interviews and site visits were reinforced by a review of the academic and policy literature. The review consisted of project reports prepared by the World Bank, Global Environment Facility, and United Nations Development Program in addition to peer- reviewed articles offering insight into climate change adaptation efforts in Bangladesh published in the past 10 years. When laying out the study below, we shift back and forth from data collected from the interviews and site visits to analysis from the literature to fit the material around our central case study (Strauss 1990)

- 3 Country background

- The authors selected Bangladesh for analysis due to its extreme vulnerability to climate related impacts. Most of Bangladesh lies in the delta of three of the largest rivers in the world – the Ganges, the Brahmaputra, and the Meghna, or GBM (Fig. 2). These rivers have a combined peak discharge of 180,000 cubic meters per second during the flood season, the second highest in the world after the Amazon and carry about two billion tons of sediments each year. Bangladesh is at risk not only to flooding and tidal inundation on the coasts, but also advanced melting of the Indian and Nepali Himalayan glaciers. This effectively means the country is hit on “both geographic sides” as well as during “both seasons:” climate change is disrupting natural cycles of rainfall and snowpack on the Tibetan Plateau which feed Bangladesh’s major rivers, and also increasing flooding, saltwater intrusion, and storm surges on the coastal belt; it is also creating excess rain during the monsoon season, and inducing a shortage of it during the winter drought (Matthews 2007; Belt 2011).

- Further compounding matters, the topography of the country is low and flat. Two-thirds of its critical infrastructure is less than 5 m above sea level and is therefore susceptible to naturally occurring river and rainwater flooding and, in lower lying coastal areas, to tidal flooding during storms. Indeed, Mirza (2002) documented that Bangladesh is perpetually at risk to four distinct types of flooding: flash floods which occur on the eastern and northern rivers, along the borders of Bangladesh, resulting from heavy rainfall; riverine floods which result when the GBM rivers or their tributaries simultaneously reach their peaks, which tend to rise and fall slowly over a 10–20 day cycle; rain floods due to high intensity local rainfall during the monsoon; and storm surge floods caused by tropical storms and cyclones which affect tidal flats and low-lying islands.

- However, once every 4–5 years, severe flooding induces substantial damage to infrastructure, housing, agriculture and livelihood. Table 1 shows serious floods in Bangladesh in the last 25 years and their impacts. A severe tropical cyclone also hits Bangladesh, on average, every 3 years resulting in extensive damage to houses, livestock, and human health (Government of Bangladesh 2005: 7). One cyclone in November 1970 produced winds as strong as 220 km per hour and a storm surge 9 m high, resulting in 300,000 (Agrawala et al. 2003) to 500,000 deaths (Thomalla et al. 2010). Another cyclone in April 1991 generated a storm surge 8 m high that displaced 11 million people and caused 138,000 deaths.

- Indeed, Bangladesh has been hit by 154 cyclones from 1877 to 1995, a rate of more than one major cyclone per year (Ali 1999), and it has also been subject to 174 separate natural disasters from 1974 to 2003 (Reid et al. 2007). Bangladesh, what one respondent even called “the most flood prone country on the globe,” experienced 21 above normal foods, four exceptional floods, and two catastrophic floods from 1954 to 2010 (Ali 1996; Chowdhury et al. 1993; Haque 1997). One flood in 1988 reduced agricultural production by 45%, and a 1998 flood resulted in the loss of more than two million hectares of arable land used for rice cultivation (Ahmed 2006). The most recent severe flood in 2007 inundated 42% of the country’s land area (62,300 square kilometers), caused 1,110 deaths, submerged 2.1 million hectares of cropland, destroyed 85,000 homes, damaged 31,000 km of roads, affected 14 million people, and induced $1.1 billion in damages (Dasgupta et al.

- Mitig Adapt Strateg Glob Change (2011) 16:845–863 849

- Fig. 2 The Ganges, Brahmaputra, and Meghna River Basins and their tributaries in Bangladesh. Source: Ahmed 2006

- 2010: 3). To put the damage in perspective, $1.1 billion is equal to all public debt listed by the government in 2008. Figure 3 illustrates how between 1954 and 2009, six major floods have inundated more than one-third of the country’s landmass. Another respondent mused that “if Bangladesh was part of a country like the United States, it would have been permanently evacuated by now.”

- 4 Bangladesh’s vulnerability to climate change

- Disturbingly, such floods and natural disasters are projected to get worse over the next few decades. A synthesis of 16 General Circulation Models and three emissions scenarios in the Intergovernmental Panel on Climate Change’s AR4 expects Bangladesh to see a temperature increases of 1–3°Celsius by 2050 (Dasgupta et al. 2010: 4). Basically, this warming will create problems associated with water: too much of it during the monsoon seasons, and too little of it during the winter. Temperature increases will likely see sea levels rise, increasing river water levels, water logging, erosion, and flooding during the monsoon; and salt water intrusion and shortages of water for irrigation and agriculture

- 850 Mitig Adapt Strateg Glob Change (2011) 16:845–863

- Table 1 Impacts of major floods in Bangladesh 1984–2007

- Year Land inundated

- (square kilometers)

- Fatalities Refugees/Homeless Damage

- (Millions of USD)

- 1984 50,000 445 378 1987 50,000 2,055 1,000 1988 85,000 6,500 45 million 1,200 1998 100,000 1,100 30 million 2,800 2004 60,000 700 15 million 6,600 2007 62,300 1,100 1.1 million 1,100

- Adapted from Government of Bangladesh 2009

- Fig. 3 Extent of above normal flooding in Bangladesh, 1950–2009. Source: Dasgupta et al. 2010: 29

- during the winter (Ahmed et al. 2010). Agrawala et al. (2003) anticipate four primary negative changes in climate and precipitation: accelerated glacier melting from increased runoff from the neighboring Himalayas, increased rainfall during the monsoon season, sea level rise leading to flooding under ambient conditions and severe flooding during storm conditions, and increased frequency and intensity of cyclones. Figure 4 shows that every area in Bangladesh is prone to at least one of these four types of floods. The academic literature and interview respondents we spoke with for this study suggested that these four causal factors will create significant damage in five key sectors in Bangladesh.

- Mitig Adapt Strateg Glob Change (2011) 16:845–863 851

- Fig. 4 Vulnerability of Bangladesh to different climate risks and flood types. Source: Mirza et al. 2003

- 852 Mitig Adapt Strateg Glob Change (2011) 16:845–863

- First, and most critical, is water resources and coastal zones. Agrawala et al. (2003) identify coastal zones as “the highest priority sector” in terms of certainty, urgency, and severity of climate-related impacts, as well as the economic importance of the resources being affected. Coastal areas comprise some 32% of the country’s total area and more than 35 million people live in coastal areas less than 1 m above sea level. Several studies indicate that the vulnerability of the coastal zone to climatic changes could worsen in the near term due to the confluence of sea level rises, subsidence, changes of upstream river discharges, cyclones and the erosion of coastal embankments (World Bank 2000).

- These pressures produce four key types of primary physical effects:

- & Saltwater intrusion: the effect of saline water intruding into estuaries and contaminating groundwater will increase as sea levels rise and river flows decrease. Water supplies for coastal agriculture, public consumption and industrial use will be severely affected. As one of the respondents noted, “Salinity encroachment towards the fresh water zone is phenomenal. Studies show that at present, almost 100 km inward salinity has encroached in the fresh water zone. We have found that in the areas where a person used to grow rice paddies, now salt is being processed. As a result there is a complete change in economic activities of these coastal communities.” & Drainage congestion: the combined effect of higher sea levels, subsidence, siltation of estuary branches, higher riverbed levels and reduced sedimentation in flood-protected areas impedes access to water for irrigation and drinking. One respondent noted that “poor drainage capacity will gradually increase water problems particularly in the coastal zone. The problem will be aggravated by the continuous development of infrastructure like roads reducing further the limited natural drainage capacity in the delta. Increased periods of inundation may hamper agricultural productivity, and will also threaten human health by increasing the potential for water borne diseases.” & Damage from natural disasters: in the coming decades, the number of coastal populations in need of annual emergency relief such as medicine and food will continue to increase as more frequent and severe climate events occur. & Coastal morphology: Bangladeshi coastal morphological processes are extremely dynamic, partly because of the tidal and seasonal variations in river flows and runoff. Climate change is expected to increase bank erosion and bed level changes in coastal rivers and estuaries, and accelerate disturbance of the balance between river sediment transport and deposition in rivers, flood plains, and coastal areas. Disturbances of the sedimentation balance will result in higher bed levels of rivers and coastal areas, which in turn will lead to higher water levels.

- Second is infrastructure and human settlements. Respondents expressed concern that high water levels in rivers surrounding polders—human made low lying tracks of land enclosed by dykes—may increase in the range of 30–80 cm, completely flooding them by 2100. Earthen embankments constructed by the Bangladesh Water Development Board are subject to erosion, and with a 45 cm rise of sea level, respondents told us they expect 15% of the land in Bangladesh to be inundated by the year 2050, resulting in more than 25 million climate refugees from the coastal districts. Indeed, during our own site visits we witnessed the flooding of villages shown in Fig. 1. Especially vulnerable in these locations would be char dwellers and women: char dwellers because they live in constantly changing islands, or chars, in the coastal district but build kacha homes made of muli bamboo, mud, and tin roofs that can be easily swept away in floods (Belt 2011; Ahmed 2008); and women because they contribute a disproportionate amount of their time rebuilding homes and caring for family members (Cannon 2002) (Fig. 5).

- Third is agriculture and food security. Bangladesh is a highly agricultural society; agriculture accounts for 63% of its labor force and 35% of its Gross Domestic Product. Rice occupies 80% of total cultivated land area but droughts during the winter season threaten all three major types: aman, aus, and jute. Adjusting is a costly option for farmers who usually need to mortgage assets or borrow money to re-sow seedlings, replace crops, pay for irrigation, or migrate. Over the past six decades, the seasonal cycle has changed dramatically, pests and diseases have increased, average temperature has increased, the winter has shortened, and Fig. 6 shows significant deviations in expected rainfall. Baas and Ramasamy (2008) predict that by 2050, dry season rainfall could decrease 37% further.

- Fig. 5 The flooded village in Boyer Char in July 2010. Source: Authors

- Mitig Adapt Strateg Glob Change (2011) 16:845–863 853

- Fig. 6 Deviation of Monsoon Rainfall from Normal Rainfall, 1961–2000. Baas and Ramasamy 2008: 26

- 854 Mitig Adapt Strateg Glob Change (2011) 16:845–863

- Anticipated higher temperatures and changing rainfall patterns, coupled with increased flooding and rising salinity in the coastal belt are likely to reduce crop yields and crop production, taking their toll on food security. The Bangladeshi government estimates that, by 2050, rice production could decline by 8% throughout the country and wheat production by 32%. In eastern Bangladesh alone the Government of Bangladesh (2009: 17) projects that 14,000 t of grain production could be lost to sea level rise in 2030 and 252,000 t lost by 2075. Ahmed and Alam (2010) assessed agricultural vulnerability to climate change in Bangladesh and concluded that drastic changes in evaporation and precipitation for both the winter and monsoon seasons were highly probable. Karim et al. (2010) calculate that a 17% loss in overall rice production and as much as a 61% decline in wheat production in the next few decades is likely; they caution that any positive increases in yield will be more than offset by moisture stress. Habibullah et al. (2010) project a significant loss of food grain production in coastal belts due to soil salinity intrusion, making affected lands unsuitable for a variety of crops. Such stark projections have been confirmed by a number of other studies (Reid et al. 2007; Ahmed 2001, 2006; Mirza et al. 2002, 2003; Paul and Rashid 1993; Faisal and Parveen 2004).

- Also, respondents expressed worry that increasing temperature could alter soil composition, further affecting crop yields. As one explained:

- Climate change can bring major changes to agricultural productivity in Bangladesh. During the last 30–40 years a typical farmer has made continuous changes in farming practice. From initially growing rice paddies, farmers have generally moved to grow wheat and then to potatoes because of declining yields over the period of time as a result of changes to temperature and soil moisture .... However only rich farmers have been able to afford such changes and marginal farmers are still following traditional practices and have not been able to sustain their livelihoods due to low yields. As a result, they are selling their lands and migrating elsewhere.

- Seasonal droughts in the country are another climatic threat to crops, causing hardship to poor agricultural laborers and others who cannot find work (Government of Bangladesh 2005: 7).

- Fourth is forestry. Bangladesh is endowed with a number of natural forest ecosystems including inland Sal forest, dipterocarp forest, savanna, bamboo bushes in the hilly regions and freshwater swamp forests (Government of Bangladesh 2005: 15). One study qualitatively analyzed the impact of climate change on forest resources of Bangladesh and found that increased rainfall during the monsoon would accelerate runoffs in forest floors instead of infiltration into the soil, causing severe erosion (Rahman and Alam 2003). Prolonged floods would severely affect growth of many timber species, causing a high incidence of mortality for Artocarpus species. Tea plantations in the northeast could also suffer from changes in moisture and humidity. The Sundarbans mangrove forest could be the most severely affected since climatic changes would alter evapotranspiration and flow rates in the winter, increasing the salinity of the soil. Respondents cautioned that eventually non-woody shrubs and bushes would replace healthy indigenous species offering dense canopy cover, and overall forest productivity would decline significantly. Coastal forests are also at grave risk to flooding and erosion, threats discussed in greater detail above, and summarized by Islam and Nandy (2001); Nandy (2003); Nandy et al. (2001, 2004); and Siddiqi (2001).

- Fifth is fisheries. Fish are a staple of Bengali culinary fare, with 80% of the daily animal protein intake in Bangladesh coming from fish and the fisheries sector contributing 3.5% to GDP (Ali 2010). Yet storm surges and increasing tidal waves from climate change could