GEFSEC Project ID: 3354

UNDP Project ID: PIMS 3598 under CPP 3138

Country: Namibia

Project Title: CPP Namibia: Adapting to Climate Change through the Improvement of Traditional Crops and Livestock Farming (CPP NAM CCA)

other project Executing Agency(ies): Ministry of Environment and Tourism & Ministry of Agriculture, Water & Forestry

GEF Focal Area: Climate Change & Land Degradation

GEF Operational Program: SPA

Starting Date: October 2005

Estimated Date of operational closure: May 2007

Estimated Date of financial closure: November 2007

pdf/ppg status report

Report submitted by:

Name					Title					      Date

Ms. Martha Mwandingi  	UNDP Nam Environment Focal Point	23 April 2007

Mr. Teofilus Nghitila		Director: Environmental Affairs, MET	23 April 2007

PART I -  PREPARATORY ASSISTANCE achievements

A- Summary of actual achievements of preparatory phase (outputs and outcomes), and explanation of any deviations from expected outcomes

The outputs of the preparatory phase of the CCA were as follows:

- Common vision among stakeholders of the concept of climate change adaptation within the context of prolonged droughts;

- Definition of the project area and its boundaries;

- Identification and selection of pilot areas and sites within the North Central region;

- Assessment of the effectiveness of current coping strategies;

- Assessment of community and household needs in terms of piloting specific adaptations;

- Assessment of institutional capacity and communication gaps in the context of early warning systems;

- Confirmation of the linkages between the project, the climate change program, the Biodiversity Strategy and Action Plan, the NDP2 and other programs;

- Identification of the institutional and organizational structures and relationships required for implementation of the project;

- Identification and confirmation of co-financing;

- Identification of the roles of government and other stakeholders in the preparation and implementation processes; and

- A Draft Medium Size Project Proposal agreed by all stakeholders for submission to the UNDP/GEF.

Table 1: Completion status of Project Activities

| Approved |  |  | Actuals |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Proposed Activities at Approval | GEF Financing | Co-financing | Status of activities | GEF financing committed | Co-financing committed | Uncommitted GEF funds |
| Preparation of the MSP document | 40,000 | 5,000 | Completed | 40,000 | 5,000 | - |
| TOTAL | 40,000 | 5,000 |  | 40,000 | 5,000 | - |

B – Record of Stakeholder Involvement in project preparation

The preparatory phase of the project entailed strategic consultation processes with key stakeholders at the national, regional and local level with the objective of:

- better understanding climate change induced impacts in north-central Namibia;

- assessing the effectiveness of current coping strategies and early warning systems;

- assessing institutional capacity, community and household needs in terms of piloting specific adaptation activities; and

- based on the above, proposing pilot sites and interventions for the MSP.

Three stakeholder consultation workshops were held, with the first being a national inception workshop, the second being a regional consultative workshop, and the third a national validation / verification workshop. All these consultations were conducted within the ambit of the CPP.

##### PART II  - PREPARATORY ASSISTANCE  financial delivery

##### Table 2 – PDF/ppg  Input Budget – Approvals and commitments

| ### Input Description* | ### Approved |  |  | ### Committed |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | ### Staff weeks | ### GEF financing | ### Co-finance | ### Staff weeks | ### GEF financing | ### Co-finance |
| ### Personnel | 8 | 4,000 | - | 6 | 3,493.58 | - |
| ### Local consultants | 6 | 18,000 | - | 8 | 27,903.66 | - |
| ### International consultants | 2 | 5,000 | - | 1.5 | 4,579.46 | - |
| Training |  | - | 5,000 |  | - | 5,000.00 |
| Printing Costs |  | 2,000 | - |  | - | - |
| Travel |  | 7,000 | - |  | 3,291.02 | - |
| Miscellaneous |  | 4,000 | - |  | - | - |
| Total | 16 | 40,000.00 | 5,000.00 | 15.5 | 39,897.72 | 5,000.00 |

Additional information as relevant:

- The delivery rate on the GEF PPG funds as at 31 December 2006 stood ninety nine point seven percent (99.7%).

- There will be US Dollars One Hundred and Two (USD 102) as unspent PDF funds at the time of financial closure.

- An additional amount of USD 9,903 was committed and disbursed for local consultants since there was an urgent need to engage the consultant team over a period of eight weeks rather than the initially planned 6 weeks. In addition, the consultant team received a total fee which was inclusive of printing, miscellaneous and some travel expenses, hence no or less amounts were committed / disbursed against these items.

Table 3: Actual PDF/PPG co-financing

| Co-financing Sources for Preparatory Assistance |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name of Co-financier (source) | Classification | Type | Amount |  |
|  |  |  | Expected ($) | Actual ($) |
| Ministry of Environment and Tourism | Executing Agency | in-kind | 5,000 | 5,000 |
| Total co-financing |  |  | 5,000 | 5,000 |

Additional information as relevant:

- No deviations from what was planned.