## Sheet1
Work Plan for In-Country Activities in Preparation for Second Regional Training on Economics of Adaptation
|  | 18 - 31 March | 1- 15 April | 16- 30 April | 1 - 15 May | 16 -31 May | 1- 15 June | 16 - 30 June | 1 -15 July | 16 - 31 July | 1-15 Aug | 16-31 Aug | SECOND REGIONAL TRAINING - SEPTEMBER
AGRICULTURE SECTOR | Review Farm Survey- Edit Desired Changes for Application in-country
Prepare sampling plan to administer survey
Conduct test surveys
Provide desired changes to survey
Conduct survey
Compile Survey Results- Prepare data for analysis
Conduct preliminary analysis in preparation for the training on analysis
WATER SECTOR | Collect hydrological information or targeted basin
Review Water Survey of users - edit desired changes for application in country
Prepare sampling plan to administer survey
Conduct test surveys
Provide desired changes to survey
Conduct survey
Compile Survey Results- Prepare data for analysis
Conduct preliminary analysis in preparation for the training on analysis
AGRICULTURE PROJECT | Determine which costs and benefits to include in the analysis
Collect annual cost and benefit data
Determine values of missing elements
In-country/online training on performing cost benefit analysis
Perform Data Cost Benefit Analysis
WATER PROJECT | Determine values of missing elements
Determine values of missing elements
In-country/online training on performing cost benefit analysis
Perform Data Cost Benefit Analysis