## Slide 1
LOGICAL FRAMEWORK – Activities design
Ms. Lucy Naydenova
Project Manager NAP-GSP support to LDCs
UN Environment

## Slide 2
Component - label for a cluster of measures to achieve the vision
Outcome - what must be in place?
Outputs - interventions/deliverables
Activities – steps to take
Terminology Refresher

## Slide 3
1.1 Enhanced capacity of Community X to mitigate climate change risks
  1.1.1 Awareness-raising campaign conducted
    1.1.1.1 Develop one leaflet…
    1.1.1.2 Deliver 3 radio-transmissions...
  1.1.2 Early-warning App developed and disseminated
    1.1.2.1 Develop an Early-Warning App connected to local weather stations..
    1.1.2.2 Install 10 billboards along main roads to promote App..
1. Resilience strengthening at community level

## Slide 4
1.1.1.1 Develop one leaflet
Task allocation:
  Communication advisor, national consultant
Partners:
  Ministry of Education
Deadline:
  Q4 Year 1
Task Allocation, Partners - Deadlines

## Slide 5
Example